## WBS with Gantt Chart
TÊN DỰ ÁN | PHẦN MỀM QUẢN LÝ SIÊU THỊ MINI
NHÓM TRƯỞNG | HUỲNH TRUNG KIÊN
DATE | [6 empty] | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE
WBS NUMBER | WBS | PRIORITY | START DATE | DUE DAtE | DURATION | % of TASK | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | WEEK 11 | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
1 | Thành lập nhóm làm đố án | Must have | 2022-12-09 | 14/09/2022 | 3 | 100%
2 | Xây dựng kế hoạch thực hiện | Must have | 15/09/2022 | 21/09/2022 | 7 | 100%
3 | Xác định các quy tắc làm việc | Must have | 22/09/2022 | 23/09/2022 | 1 | 100%
4 | Lập kế hoạch dự phòng | Must have | 24/09/2022 | 27/10/2022 | 3 | 100%
5 | Xây dựng tài liệu mô tả | Must have | 28/10/2022 | 2022-02-10 | 6 | 40%
6 | Xác định yêu cầu hệ thống | Must have | 2022-04-10 | 2022-06-10 | 3 | 100%
7 | Xác định các đối tượng quan trọng | Must have | 2022-07-10 | 2022-09-10 | 3 | 60%
8 | Mô tả các chức năng qua các sơ đồ | Must have | 2022-10-10 | 14/10/2022 | 5 | 0%
9 | Xác định cấu trúc, thành phần | Must have | 15/10/2022 | 17/10/2022 | 3 | 0%
10 | Thiết kế giao diện | Must have | 18/10/2022 | 22/10/2022 | 5 | 0%
11 | Thiết kế chức năng | Must have | 23/10/2022 | 27/10/2022 | 5 | 0%
12 | Thiết kế cơ sở dữ liệu | Must have | 28/10/2022 | 31/10/2022 | 4 | 0%
13 | Phát triển và kiểm tra | Must have | 2022-01-11 | 2022-04-11 | 5 | 0%
14 | Xây dựng chi tiết hệ thống | Must have | 2022-05-11 | 2022-08-11 | 4 | 0%
15 | Kiểm tra các module và tích hợp | Must have | 2022-09-11 | 2022-12-11 | 5 | 0%
16 | Cài đặt hệ thống | Must have | 13/11/2022 | 15/11/2022 | 3 | 0%
17 | Bảo trì | Must have |  |  |  | 0%
18 | Nâng cấp, mở rộng hệ thống | Must have |  |  |  | 0%

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.